## Sheet1
Issue Log Date: 26-June-2023
Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments
1 | Oracle exception occurred when registering the user. | Unable to add new users. | 2023-06-09 | Asritha Baddam | Pydi Venkata Satya Ramesh Adapa | H | 2022-06-10 | Closed | The DB package now includes additional User Input. That was removed and updated. Working properly at the moment.
2 | In the admin page, the data is not populating correctly. | Access the admin data. | 2023-06-14 | Jaya Lakshmi Medikonda | Divya Sree Vadlakonda | M | 2023-06-17 | Closed | Mismatched attributes in the API integration. Checked and updated. Working exactly as expected.
3 | Receiving a pop-up warning for mandatory fields on the customer registration page. | Unable to update customer information. | 2023-06-21 | Nishanth Raju Saraswathi | Asritha Baddam | L | 2023-06-24 | Closed | Published after making the necessary logical corrections. Working properly at the moment.
4 | Order tracking is not functioning as intended. | Unable to track the order properly. | 2023-06-22 | Pydi Venkata Satya Ramesh Adapa | Nishanth Raju Saraswathi | H | 2023-06-23 | Closed | The Maps service is not working. The service was restarted. The functionality is now as expected.
5 | When attempting to save changes, the trainer page throws an exception. | In the trainer page, saving is not possible. | 2023-06-23 | Divya Sree Vadlakonda | Syam Kumar Allaparthi | H | 2023-06-27 | Closed | The logic does not address the null exception. Updated and made readily accessible. Now working as expected.
6 | Unable to send emails associated with promotions. | Customers have not been informed of any promotions or discounts. | 2023-06-24 | Syam Kumar Allaparthi | Jaya Lakshmi Medikonda | M | 2023-06-27 | Closed | An SMTP service issue. Checked and resolved. Works perfectly now.