## Sheet1
Project Name: Vindhu-World of Taste Restaurant Website |  | Presented by: Group1 |  | Date: | 2023-06-15
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 25 | 15 | 375 |  |  | $- | 375 |  | 375
2. Planning | 5 | 15 | 75 |  |  | $- | 75 |  | 75
3. Executing |  |  | $- |  |  | $- | $- |  | $-
3.1 Course design and development |  |  | $- |  |  | $- | $- |  | $-
3.1.1 Supplier management training | 5 | 15 | 75 | 5 | 15 | 75 |  | 550 | 550
3.1.2 Negotiating skills training | 5 | 15 | 75 | 5 | 15 | 75 | 150 | 550 | 700
3.1.3 Project management training | 5 | 15 | 75 | 5 | 15 | 75 | 150 | 550 | 700
3.1.4 Software applications training | 5 | 90 | 450 | 5 | 90 | 450 | 900 | 3000 | 3900
3.2 Course administration | 5 | 30 | 150 | 5 | 30 | 150 | 300 | 2600 | 2900
3.3.Course evaluation | 25 | 10 | 250 |  |  | $- | 250 |  | 250
3.4 Stakeholder communications | 10 | 80 | 800 |  |  | $- | 800 |  | 800
4. Monitoring and Controlling | 25 | 60 | 1500 |  |  | $- | 1500 |  | 1500
5. Closing | 25 | 10 | 250 |  |  | $- | 250 |  | 250
Subtotal | [8 empty] | 12000
Reserves |  |  | $- |  |  | $- | $- |  | 1500
Total | 140 |  | 4075 | 25 | 165 | 825 | 4750 | 7250 | 13500
Assumptions: We are expecting our overall budget around 12000$ with reserves at 11.11 % which accounts to total of 13500$